## Sheet1
release	change	new KEP?	Description	What needs to be done?	why?	Links
1.22	fix	no	Fix shared pool reporting	KEP edit, PR with fixes, e2e test update	bugfix	https://github.com/kubernetes/enhancements/pull/2201 https://github.com/kubernetes/kubernetes/issues/102190 https://github.com/kubernetes/kubernetes/pull/97415
1.23	change	no	Promote GetAllocatableResources to beta	KEP edit, e2e test update	regular graduation process
1.24	change	no	Promote GetAllocatableResources to stable	KEP edit	regular graduation process
1.24	enhancement	yes	Watch + Watchallocatable endpoints	KEP, implementation PR	address acknowledged scalability/performance concern
1.25	change	no	Watch + Watchallocatable endpoints to beta	KEP edit, e2e tests (update at least)	regular graduation process
1.27	change	no	Watch + Watchallocatable endpoints to stable	KEP edit	regular graduation process